## Attack Surface
Component | Entry Point | Threat | Risk Level | Control | Status | Owner | Last Reviewed | Notes | Risk Score
API /generate | POST | Prompt Injection | High | Input Sanitization | Pending | Sankar | Ken | Okay | 3
Logging | File logs | Data Leakage | High | Mask sensitive data | In Progress |  |  |  | 3 | Don't edit red cells
LLM Output | Response | Info Exposure | Medium | Output filtering | Ignored |  |  |  | 2
Auth | Token | Token leakage | High | Secure storage | Pending |  |  |  | 3
Rate Limit | API | Abuse | High | Rate limiting | Pending |  |  |  | 3
Input | Prompt | Overlong input | Medium | Length checks | Pending |  |  |  | 2
Headers | HTTP | Missing headers | Medium | Security headers | Pending |  |  |  | 2
LLM | System prompt | Leakage | High | Prompt isolation | Pending |  |  |  | 3
Storage | DB | Sensitive storage | High | Encryption | Pending |  |  |  | 3
Logs | Debug | Secrets in logs | High | Masking | Pending |  |  |  | 3
API | GET | Open endpoint | Medium | Auth required | Pending |  |  |  | 2
Model | Response | Hallucination leak | Medium | Validation | Pending |  |  |  | 2
Cache | Layer | Data exposure | Medium | Cache control | Pending |  |  |  | 2
Env | Config | Key exposure | High | Env vars | Pending |  |  |  | 3
File Upload | Endpoint | Malicious file | High | Validation | Pending |  |  |  | 3
Session | Token | Session hijack | High | Secure cookies | Pending |  |  |  | 3
Prompt | User input | Instruction override | High | Sanitization | Done |  |  |  | 3
LLM | Output | Sensitive pattern | Medium | Filtering | Pending |  |  |  | 2
API | POST | No validation | High | Schema validation | Pending |  |  |  | 3
Monitoring | Logs | No alerts | Medium | Alerting | Pending |  |  |  | 2
Docker | Container | Misconfig | Medium | Secure config | Pending |  |  |  | 2
Network | Traffic | MITM risk | High | HTTPS | Pending |  |  |  | 3
Auth | Login | Weak auth | High | Strong auth | Pending |  |  |  | 3
Input | Encoding | Bypass filters | Medium | Decode & check | Pending |  |  |  | 2
System | Config | Debug exposed | High | Disable debug | Pending |  |  |  | 3

## Dashboard
Metric | Value
Total Issues | 25 | Don't edit red cells
High Risk | 15
Pending | 22
Completed | 1

## About
Developed by Sankar Srinivasan
petra.srini@gmail.com
https://beacons.ai/sankarsrinivasan
Don't edit red cells
This excel sheet is part of the book:
API Security for AI Applications